## Zeitplan Bachelorarbeit
| Week | Timeline Master Thesis
|  | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4 |  |  |  | Month 5 |  |  |  | Month 6
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
Setup Phase | bar: Month 1 1
Create and manage testing environment | bar: Month 1 1
Create benchmark datasets | bar: Month 1 1
Research and Experiments | bar: Month 1 2 to Month 5 19
1 | Development of multimodal Data2Vec | bar: Month 1 2 to Month 1 4
1 | Benchmarking and refinement | bar: Month 2 5 to Month 2 8
2 | Experiments on latent space (representations) | bar: Month 3 9 to Month 3 11
3 | Development of multimodal Variational Autoencoder | bar: Month 3 12 to Month 4 16
3 | Latent-Space Arithmetic | bar: Month 4 16 to Month 5 19
Writing | bar: Month 3 11 to Month 6 21
Theory and Methodology | bar: Month 3 11 to Month 4 14
Research and Experiments | bar: Month 4 14 to Month 5 19
Introduction | bar: Month 5 20
Outlook and Conclusion | bar: Month 6 21
Finalization | bar: Month 6 22 to Month 6 24
Format checks | bar: Month 6 22
Proof reading | bar: Month 6 22 to Month 6 23
Plagiarism check | bar: Month 6 23
Last checks and buffer | bar: Month 6 24